## Testcases
UserStory | Testcase | Input | Output | Acceptance Criteria | Status | Sizes | Error description | Comments
Login | 0 |  |  | 1)One Session 2)Username and password fit with registration 3)Feedback of Success | Open |  |  | TestCase 0 is always a summary of the information stored in the user story
Login | 1 | Correct user name/password | Feedback for succesfull login | 2) + 3) | OK | SmallScreen/Low Density |  | Implicitly tests Input fields username, password and login button
Login | 1 | Correct user name/password | Feedback for succesfull login | 2) + 3) | Open | NormalScreen/High Density |  | Implicitly tests Input fields username, password and login button
Login | 1 | Correct user name/password | Feedback for succesfull login | 2) + 3) | OK | Extra Large Screen/Extra High Density |  | Implicitly tests Input fields username, password and login button
Login | 2 | Correct user name/wrong password | Feedback that login information was not correct | 2) | OK | SmallScreen/Low Density |  | If username does not exist on DB no login possible
Login | 3 | Wrong user/correct password | Feedback that login information was not correct | 2) | OK | SmallScreen/Low Density |  | Feedback that username does not exist
Login | 3 | Wrong user/correct password | Feedback that login information was not correct | 2) | OK | NormalScreen/High Density |  | Feedback that username does not exist
Login | 4 | Wrong user/wrong password | Feedback that login information was not correct | 2) | OK | SmallScreen/Low Density |  | Feedback that username does not exist
Login | 4 | Wrong user/wrong password | Feedback that login information was not correct | 2) | Error | LargeScreen/Medium Density | Buttons could be bigger | Feedback that username does not exist
Login | 5 | Press Login Button with correct data | Feedback for succesfull login + DisplayMainView | 3) | OK | SmallScreen/Low Density
Login | 6 | Press Register Button | Display RegisterView | 3) | Open
Login | 6 | Press Register Button | Display RegisterView | 3) | Error | NormalScreen/High Density | Buttons not according corporate layout (Pink/text white); Labels should be pink? | Corporate layout must be defined
Login | 6 | Press Register Button | Display RegisterView | 3) | Error | LargeScreen/Medium Density | Buttons not according corporate layout (Pink/text white); Labels should be pink? Buttons to small | Corporate layout must be defined
Login | 6 | Register with not matching password | Information is displayed | 3) | OK | NormalScreen/High Density
Login | 6 | Register with already existing Username | Information is displayed/Registration not possible | 3) | OK | Extra Large Screen/Extra High Density
Login | 6 | Register with filling in all fields | Information is displayed | 3) | OK | NormalScreen/High Density
Login | 6 | Create new account | Account created screenflow to main view | 3) | OK | NormalScreen/High Density
Login | 6 | Create new account | Account created screenflow to main view | 3) | OK | Extra Large Screen/Extra High Density
Login | 7 | Press Login button with no username and password given | Feedback that login information need to be entered | 3) | Error | LargeScreen/Medium Density | Message according to register view with information that fields must be filled is needed
MainScreen | 8 | Incomming Navigation from Login/Register | Table with recent receipts displayed |  | Error | SmallScreen/Low Density | Table header not properly displayed | Functionality to read receipts not implemented
MainScreen | 8 | Incomming Navigation from Login/Register | Table with recent receipts displayed |  | OK | NormalScreen/High Density |  | Functionality to read receipts not implemented
MainScreen | 8 | Incomming Navigation from Login/Register | Table with recent receipts displayed |  | Error | LargeScreen/Medium Density | Text in table header could be bigger | Functionality to read receipts not implemented
MainScreen | 9 | Navigation to Reports by clicking on the table | Report view displayed |  | Error | SmallScreen/Low Density | Table header not properly displayed
MainScreen | 9 | Navigation to Reports by clicking on the table | Report view displayed |  | OK | NormalScreen/High Density
MainScreen | 9 | Navigation to Reports by clicking on the table | Report view displayed |  | OK | LargeScreen/Medium Density | Table header not properly displayed
MainScreen | 9 | Navigation to Reports by clicking on the table | Report view displayed |  | OK | Extra Large Screen/Extra High Density | Table header not properly displayed
MainScreen | 10 | Navigation to Camera by clicking on SCAN | Camera displayed |  | OK | SmallScreen/Low Density
MainScreen | 10 | Navigation to Camera by clicking on SCAN | Camera displayed |  | OK | NormalScreen/High Density
MainScreen | 10 | Navigation to Camera by clicking on SCAN | Camera displayed |  | OK | LargeScreen/Medium Density
MainScreen | 10 | Navigation to Camera by clicking on SCAN | Camera displayed |  | OK | Extra Large Screen/Extra High Density
Edit View | 11 | View displayed with extracted data | Extracted data displayed |  | Error | SmallScreen/Low Density | Display not correct
Edit View | 11 | View displayed with extracted data | Extracted data displayed |  | Error | NormalScreen/High Density | Display not correct/Burger Navigation not displayed
Edit View | 11 | View displayed with extracted data | Extracted data displayed |  | Error | LargeScreen/Medium Density | Burger Navigation not displayed
Edit View | 11 | Rescan receipt | Screenflow back to camera |  | OK | NormalScreen/High Density
Edit View | 11 | Rescan receipt | Screenflow back to camera |  | OK | LargeScreen/Medium Density
Edit View | 12 | Change Data | Manually change of the data. Various tests |  | Error | SmallScreen/Low Density | 1) Amount must be separated by "." not "," 2) Date format not locallized (Expected format dd/mm/yyyy). Format check OK
Edit View | 13 | Save Data | Save receipt data |  | OK | SmallScreen/Low Density | OK for changed data. NOK when no data is given.
Edit View | 13 | Save Data | Save receipt data |  | OK | NormalScreen/High Density | OK for changed data. NOK when no data is given.
Edit View | 13 | Save Data | Save receipt data |  | OK | LargeScreen/Medium Density | OK for changed data. NOK when no data is given.
Edit View | 13 | Save Data | Save receipt data |  | OK | Extra Large Screen/Extra High Density | OK for changed data. NOK when no data is given.

## FixedValues
Open
OK
Error