## PB
ID | Epic | PBI | Description | Acceptance Criteria | Dependency | Effort | Moscow | Value | Risk | Kano | Done | Technical Objects
1 | Login | UseCase Creation | As User I want to log me into ShopAdmin syncronize my acount. | One Session Username and Password fit with registration Feedback of success |  | 1 | must | 5 | 1 | mandatory | Yes
2 | Login | Screen MokUp | Buttons, Textfields and Buttons are shown. | Picture(PNG, JPEG, etc) available |  | 1 | must | 3 | 1 | mandatory | Yes
3 | Login | Implement Activity | Existing layout and acitivity for registration will be reused. So far that not needed register fields are hidden. | User interaction on screenelements is properly handled. Switch between Login/Register is working. | Screen MokUp available. Layout/Activity Register is available. | 2 | must | 8 | 1 | mandatory | Yes | Login_Register_Activity.java activity_login_register.xml
4 | Login | Implement Controller | Controller class encapsulates the business logic of the corresponding activity class. I.e. access to database functions. | Dataflow and interactions between activity screenelements and controller is complete. After login session is created in Statics-Class | Activity class and database functions available. Session functionality available in Statics-Class | 2 | must | 13 | 5 | mandatory | Yes | RegisterControllerImpl.java
5 | Login | Implement Database functions | Needed database functions for login is to provide access to user data (username and password) | Funtions to read user data from database implemented. | Database table for user data and access functions | 2 | must | 13 | 5 | mandatory | Yes | DatabaseModel.java DatabaseController.java
6 | Login | Test | Developer test, define test-cases for integration test, implement instrumentation/unit test. | Use Case requirements succesfully tested. | Use Case available. Implementation consistent. | 1 | must | 5 | 1 | mandatory | No
7 | Login | Doku | Minimal Java-Doc completed, document key concepts of component. | Java-Doc available. |  | 1 | must | 1 | 1 | mandatory | No
8 | Registration | UseCase Registration | As User I want make a Registration, to use all functions of ShopAdmin. | Persistent Password Username Feedback of success |  | 1 | must | 5 | 1 | mandatory | Yes
9 | Registration | Screen MokUp | Buttons, Textfields and Buttons are shown. | Picture(PNG, JPEG, etc) available |  | 1 | must | 3 | 1 | mandatory | Yes
10 | Registration | Implement Activity | Main deliverables are the layout file and the corresponding activity class. Within the activity the view logic for the screenelements (button handlers etc.) is implemented. | User interaction on screenelements is properly handled. Switch between Login/Register is working. | Screen MokUp available. | 2 | must | 8 | 1 | mandatory | Yes | Login_Register_Activity.java activity_login_register.xml
11 | Registration | Implement Controller | Controller class encapsulates the business logic of the corresponding activity class. I.e. access to database functions. | Dataflow and interactions between activity screenelements and controller is complete. After registration session is created in Statics-Class | Activity class and database functions available. Session functionality available in Statics-Class | 2 | must | 13 | 5 | mandatory | Yes | RegisterControllerImpl.java
12 | Registration | Implement Database functions | Needed database functions for register is to provide read access to user data (username and password) as well as the possibility to create a new account | Functions to check availability of given username and functions to create new account. | Database table for user data, access and write functions. | 2 | must | 13 | 5 | mandatory | Yes | DatabaseModel.java DatabaseController.java
13 | Registration | Test | Developer test, define test-cases for integration test, implement instrumentation/unit test. | Use Case requirements succesfully tested. | Use Case available. Implementation consistent. | 1 | must | 5 | 1 | mandatory | No
14 | Registration | Doku | Minimal Java-Doc completed, document key concepts of component. | Java-Doc available. |  | 1 | must | 1 | 1 | mandatory | No
15 | Scan Receipt | UseCase Scan | As User I want to scan a receipt to store the information of my purchases | Foto with handy camera Show results |  | 1 | must | 5 | 1 | mandatory
16 | Scan Receipt | Implement Activity | Activity reuses build in camera module without its own layout file. This needs to be taken into consideration for screen flow (back). | Build in camera displayed and available functions reused. |  | 1 | must | 3 | 1 | mandatory | Yes | CameraActivity.java
17 | Scan Receipt | Implement Controller | Controller class is the interface between the build in camera and the tesseract engine. Furthermore controller provides access to the extracted data for edit view. | Taken picture is temporarily stored on filesystem (if needed) and passed to tesseract | Activity class available. Tesseract engine available. | 5 | must | 40 | 13 | mandatory | No | CameraController.java
18 | Scan Receipt | Test | Developer test, define test-cases for integration test, implement instrumentation/unit test. | Use Case requirements succesfully tested. | Use Case available. Implementation consistent. | 1 | must | 13 | 1 | mandatory | No
19 | Scan Receipt | Doku | Minimal Java-Doc completed, document key concepts of component. | Java-Doc available. |  | 1 | must | 8 | 1 | mandatory | No
20 | Edit Scan Results | UseCase Edit Scan Results | As a user I want to be able to alter the scanned receipt data before save. | Ability to modify result data |  | 1 | must | 5 | 1 | mandatory | Yes
21 | Edit Scan Results | Screen MokUp | Buttons, Textfields and Buttons are shown. | Picture(PNG, JPEG, etc) available |  | 1 | must | 3 | 1 | mandatory | Yes
22 | Edit Scan Results | Implement Activity | Main deliverables are the layout file and the corresponding activity class. Within the activity the view logic for the screenelements (button handlers etc.) is implemented. | User interaction on screenelements is properly handled. | Screen MokUp available. | 2 | must | 8 | 1 | mandatory | Yes
23 | Edit Scan Results | Implement Controller | Controller class encapsulates the business logic of the corresponding activity class. I.e changing the data on the layout, saving the data in database. | Dataflow and interactions between activity screenelements and controller is complete. Data can be stored in database | Activity class and database functions available. | 3 | must | 13 | 1 | mandatory | Yes
24 | Edit Scan Results | Implement Database functions | Needed database functions to save receipt data. | Functions to store new receipt data. | Database table for receipt data and write functions. | 3 | must | 13 | 1 | mandatory | No
25 | Edit Scan Results | Test | Developer test, define test-cases for integration test, implement instrumentation/unit test. | Use Case requirements succesfully tested. | Use Case available. Implementation consistent. | 1 | must | 3 | 1 | mandatory | No
26 | Edit Scan Results | Doku | Minimal Java-Doc completed, document key concepts of component. | Java-Doc available. |  | 1 | must | 3 | 1 | mandatory | No
27 | Show Reports | UseCase Show Reports | As User I want to see all results from a specific timeline, to see my purchase history. | show table of results define timeline |  | 1 | must | 5 | 1 | mandatory | No
28 | Show Reports | Sceen MokUp | Buttons, Textfields and Buttons are shown. | Picture(PNG, JPEG, etc) available |  | 1 | must | 3 | 1 | mandatory | No
29 | Show Reports | Implement Fragment framework | Various base forms of reports should be accessible to the user. Between those reports convenient changes need to be possible. New reports need to be included in fragment framework. | Sliding between different reports is possible. All existing reports must be accessible. |  | 3 | must | 20 | 1 | mandatory | Yes | ReportPagerAdapter.java ReportController.java
30 | Show Reports | Report requirements | Document complete report requirements. Define Base reports: - Shop, Category, Group Summarys and further summarys. Specification includes displayable columns - Define suitable filter criterias. I.E. Timeline. For all or specific reports - Input conecpt for filter criterias - Define Sorting requirements for tables | Requirements documented. Implementation can be started. | Database table for receipt data. | 5 | must | 13 | 1 | mandatory | No
31 | Show Reports | Fragment report for shop summary | Creation of a corresponding layout file and implementation of a fragment class. | View logic for report. | Fragment framework. Read functionality for receipt data and Container class for receipt data. | 2 | must | 8 | 1 | mandatory | Yes | ReportShopSummaryFragment.java
32 | Show Reports | Fragment report for category summary | Creation of a corresponding layout file and implementation of a fragment class. | View logic for report. | Fragment framework. Read functionality for receipt data and Container class for receipt data. | 2 | must | 8 | 1 | mandatory | Yes | ReportCategorySummaryFramgent.java
33 | Show Reports | Implement Controller | Within the controller class the receipt data for the corresponding user is retreived from the database. According to the currently active page fragment the receipt data is sorted, grouped accordingly. | Table data for display is created (including header file) and passed to view. | Database table and read functions for receipt data and container class. Corresponding report fragment. | 8 | must | 20 | 1 | mandatory | Yes | ReportController.java
34 | Show Reports | Implement Database functions | Needed database functions to read the receipt data for the actual user. | Functions to read all receipt data for the current user. |  | 3 | must | 13 | 1 | mandatory | No | DatabaseModel.java DatabaseController.java
35 | Show Reports | Test | Developer test, define test-cases for integration test, implement instrumentation/unit test. | Use Case requirements succesfully tested. | Use Case available. Implementation consistent. | 3 | must | 3 | 1 | mandatory | No
36 | Show Reports | Doku | Minimal Java-Doc completed, document key concepts of component. | Java-Doc available. |  | 2 | must | 3 | 1 | mandatory | No
37 | Logout | UseCase Logout | As a user I want to be able to push a logout button | Button available Login after Logout necessary |  | 1 | should | 3 | 1 | indifferent | No
38 | Logout | Integrate into Burger Navigation |  |  |  | 2 | should | 8 | 1 | indifferent | No
39 | Logout | Test |  |  |  | 1 | should | 3 | 1 | indifferent | No
40 | Logout | Doku |  |  |  | 1 | should | 3 | 1 | indifferent | No
41 | Verify Data | Obsolete |  |  |  | 4 | could | 5 | 1 | questionable | No
42 | Rescan Receipt | UseCase Rescan Receipt | As a user I want to be able to rescan a receipt to fix bad quality pictures | Business value must be entered Try to use user story format to improve an understanding of what, for who and why this requirement is needed |  | 1 | could | 3 | 1 | mandatory
43 | Rescan Receipt | Implement Controller |  |  |  | 1 | could | 5 | 1 | mandatory | No | CameraController.java
44 | Rescan Receipt | Implement Dataflow |  |  |  | 3 | should | 8 | 1 | mandatory | No | CameraController.java
45 | Rescan Receipt | Test |  |  |  | 1 | could | 5 | 1 | mandatory | No
46 | Rescan Receipt | Doku |  |  |  | 1 | could | 5 | 1 | mandatory | No
47 | Show Detailed receipt results | UseCase Show Detailed receipt results | As User I want to see a detailed receipt result of one scan. | Out of compressed table results single results must be accessible |  | 1 | should | 3 | 1 | excitment | No
48 | Show Detailed receipt results | Implement Controller | Within the controller class the details of one receipt must be displayed. Therefore the EditView can be reused without the possibility to change the receipt data. Furthermore the ScreenFlow needs to be adjusted. | Receipt can be displayed without the possibility to change data. ScreenFlow leads back to calling activity. |  | 5 | should | 8 | 2 | excitment | No | EditControllerImpl.java
49 | Show Detailed receipt results | Test | Developer test, define test-cases for integration test, implement instrumentation/unit test. | Use Case requirements succesfully tested. | Use Case available. Implementation consistent. | 1 | should | 3 | 1 | excitment | No
50 | Show Detailed receipt results | Doku | Minimal Java-Doc completed, document key concepts of component. | Java-Doc available. |  | 1 | should | 3 | 1 | excitment | No
51 | Create Filter | UseCase CreateFilter | As User I want to define a filter to show specific results, applied to that filter. | specify filter for days, weeks, months, years, brand, category, etc |  | 1 | must | 5 | 1 | mandatory | No
52 | Create Filter | Implement Controller | According to the specified requirements the user needs a possibility to specify and change the current filter. According to the given Input the corresponding report controllers need to be enhanced. | The given filter criterias are applied to the shown results. | Report requirements Report Fragments | 5 | must | 20 | 5 | mandatory | No | TBD
53 | Create Filter | Test | Developer test, define test-cases for integration test, implement instrumentation/unit test. | Use Case requirements succesfully tested. | Use Case available. Implementation consistent. | 1 | must | 5 | 1 | mandatory | No
54 | Create Filter | Doku | Minimal Java-Doc completed, document key concepts of component. | Java-Doc available. |  | 1 | must | 3 | 1 | mandatory | No
55 | Save Scan Results | UseCase Save Scan Results | As User I want to save the taken picture with the recognized results, to review my receipts. (Respecification needed) | Ability to review results save results in database feedback of successful save | Respecification needed | 1 | should | 13 | 8 | questionable | No
56 | Burger Navigation | Define Vision | Creation of a common usage principle to integrate into all activities and design principle for the burger button | Guideline-Dokument including requirements |  | 3 | should | 8 | 1 | excitment | No
57 | Burger Navigation | MokUp | MokUp Dokument for the Navigation (including Titles and Menu) | Dokument available |  | 2 | should | 3 | 1 | excitment | No
58 | Burger Navigation | Specify Interface to Activities | Specificaion of a technical guideline to introduce the Buger Button to the activities | Dokument available |  | 3 | should | 5 | 1 | excitment | No
59 | Burger Navigation | Special Activities: Change Account | Checking the need of a activity to change the given account data | Requirements and UseCase available |  | 2 | could | 5 | 1 | excitment | No
60 | Burger Navigation | Special Activities: Configure | Checking the need of an activity to technically configure the App (i.e. clean up database to release consumed storage capacity or to setup internet database) | Requirements and UseCase available |  | 2 | could | 5 | 1 | excitment | No
61 | Burger Navigation | Special Activities: Group Handling | Checking the need of an activity for the group administration (i.e. add new user, delete current user) | Requirements and UseCase available |  | 2 | could | 5 | 1 | excitment | No
62 | Burger Navigation | Test | Developer test, define test-cases for integration test, implement instrumentation/unit test. | Use Case requirements succesfully tested. | Use Case available. Implementation consistent. | 1 | could | 3 | 1 | excitment | No
63 | Burger Navigation | Doku | Minimal Java-Doc completed, document key concepts of component. | Java-Doc available. |  | 1 | could | 3 | 1 | excitment | No
64 | Image Processing | Specify Requirements | Creation of the special requirements document regarding image processing | Requirement Document available and handed over |  | 3 | must | 13 | 8 | mandatory | Yes
65 | Image Processing | Establish Tesseract in App | All developers need to setup the tesseract functionality locally in android app to include tesseract library. | Tesseract can be accessed and commited |  | 8 | must | 40 | 13 | mandatory | No | TBD
66 | Image Processing | Implement Classifier | Implementation of a java-class containing the algorithm to classify the extracted picture data. | Extracted data can be classified as specified in requirement document. |  | 8 | must | 40 | 13 | mandatory | No | TBD
67 | Image Processing | Test | Developer test, define test-cases for integration test, implement instrumentation/unit test. | Use Case requirements succesfully tested. | Use Case available. Implementation consistent. | 3 | must | 13 | 5 | mandatory | No
68 | Image Processing | Doku | Minimal Java-Doc completed, document key concepts of component. | Java-Doc available. |  | 3 | must | 13 | 5 | mandatory | No
69 | Corporate Layout | Image Creation (Pigs, …) | Creation of resources for the app. | Images available |  | 5 | should | 5 | 1 | excitment | Yes
70 | Corporate Layout | Evaluate Display Strategy | Specification of display strategy regarding the user interface components. Requirements regarding size of user interface elements on large, medium and small mobiles. Also a strategy regarding landscape and portrait mode is needed. | Dokument available |  | 8 | must | 20 | 5 | mandatory | No
71 | Corporate Layout | Create Corporate Design | Creation of a corporate design document specifying fonts, colors and margins. | Dokument available |  | 8 | should | 20 | 5 | mandatory | No
72 | Corporate Layout | Specify Implementation Guide | Display strategy and corporate design can be implemented in various way (i.e. resource files or programmatically). After specifications are complete a common implementation guideline is needed | Dokument available | Display Strategy Corporate Design | 5 | should | 13 | 5 | mandatory | No
73 | Group Scenario | GroupScenario UseCase | As a user I want to be part of a group sharing receipt data. | As a user I can join one group and I can leave the group. |  | 5 | should | 13 | 5 | excitment | No
74 | Group Scenario | Design Database requirments | Regarding group functionality the requirements regarding the database shema needs to be clarified. | Requirment-Dokument available |  | 5 | should | 13 | 5 | excitment | No
75 | Group Scenario | Dataflow | Specification regarding dataflow between local and internet db to share common receipt data. | Requirment-Dokument available |  | 8 | should | 13 | 5 | excitment | No
76 | Group Scenario | Test | Developer test, define test-cases for integration test, implement instrumentation/unit test. | Use Case requirements succesfully tested. | Use Case available. Implementation consistent. | 1 | should | 5 | 1 | excitment | No
77 | Group Scenario | Doku | Minimal Java-Doc completed, document key concepts of component. | Java-Doc available. |  | 1 | should | 5 | 1 | excitment | No
78 | Database | Container Classes | Container Classes must be implemented for user and receipt data. | Implementation complete. |  | 5 | must | 13 | 1 | mandatory | No | User.java Receipt.java
79 | Database | Table Diagramm | Create documentation of the table shema of the database | Dokument available |  | 3 | must | 8 | 1 | mandatory | No
80 | Project Management | Product Backlog Refinement | Constantly check and update product backlog items. | Produkt backlog up to date and individual user stories ready for implementation in the next sprint. |  | 5 | must | 8 | 1 | mandatory | No
81 | Project Management | Create Manual | Creation of a manual document for the user. Probably accessible via the burger navigation | Dokument available and accessible by the user. |  | 5 | must | 8 | 1 | mandatory | No
82 | Project Management | Create Status Report | Creation of presentations or documents for status reports | Dokuments sent |  | 5 | must | 8 | 1 | mandatory | No
83 | Project Management | Create Overall Dokumentation | Creation of final presentation and documentation for handover. | Dokuments sent |  | 8 | must | 13 | 1 | mandatory | No
84 | Login | Session Handling | Concept for Session handling | Documentation available |  | 5 | should | 5 | 1 | mandatory | No
85 | Database | Advanced Database concept | Specification on how the dataflow between the local and a possible internet database could be realized | Documentation available |  | 5 | could | 20 | 1 | excitment | No
86 | Corporate Layout | Build Display Strategy for Small Mobiles | Small Layouts for all views must be implemented | Layouts - activityEdit.xml - activityLoginRegister.xml - activityMain.xml - activityReports.xml - report_fragment_category_summary.xml - report_fragment_shop_summary.xml available and developer tested. |  | 5 | should | 3 | 1 | excitment | No | activityEdit.xml activityLoginRegister.xml activityMain.xml activityReports.xml report_fragment_category_summary.xml report_fragment_shop_summary.xml
87 | Corporate Layout | Build Display Strategy for Large Mobiles | Large Layouts for all views must be implemented | Layouts - activityEdit.xml - activityLoginRegister.xml - activityMain.xml - activityReports.xml - report_fragment_category_summary.xml - report_fragment_shop_summary.xml available and developer tested. |  | 5 | should | 3 | 1 | excitment | No | activityEdit.xml activityLoginRegister.xml activityMain.xml activityReports.xml report_fragment_category_summary.xml report_fragment_shop_summary.xml
88 | Corporate Layout | Build Display Strategy for Xlarge Mobiles (Tablets) | Xlarge Layouts for all views must be implemented | Layouts - activityEdit.xml - activityLoginRegister.xml - activityMain.xml - activityReports.xml - report_fragment_category_summary.xml - report_fragment_shop_summary.xml available and developer tested. |  | 5 | could | 3 | 1 | excitment | No | activityEdit.xml activityLoginRegister.xml activityMain.xml activityReports.xml report_fragment_category_summary.xml report_fragment_shop_summary.xml
| Project Management | Refactoring | Regarding codereview collect locally possibilities (wihtin code) for refactoring | Local List available |  | 3 | could | 5 | 1 | performance | No
| Project Management | Testsupport | Additional general tests supporting tests. I.E. evaluate Android Monitor | Git Issues created |  | 8 | should | 3 | 1 | mandatory | No
| Corporate Layout | Screenflow | Additional Screenflow Requirements regarding Return Button | Return button behaves correct… |  | 3 | could | 3 | 1 | excitment | No

## Festwerte
Moscow | Value | Risk | Kano
must | 0 | 0 | excitment
should | 0.5 | 0.5 | indifferent
could | 1 | 1 | mandatory
wont | 2 | 2 | performance
| 3 | 3 | questionable
| 5 | 5 | reverse
| 8 | 8
| 13 | 13
| 20 | 20
| 40 | 40
| 100 | 100

## Ticket
ID(in GIT) | Issue | Technical Component
1 | Overview not scaled right in Emulator | MainActivity/Controller
2 | Sum not displayed in overview | MainActivity/Controller
3 | Menu not implemented | ???
4 | Error when Camera opens, libwvm.so failed to open | CameraView
5 | onPollAlarm problem | ???
6 | Spinner error | EditActivity/Controller
7 | Double entries | ???